## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Code Things…
Create a collection | Create an issue class w/ tests | 1 | /
Create a collection | Create a series class that holds issue items w/ tests | 1 | /
Create a collection | Create a collection class that holds series items w/ tests | 1 | /
Create a collection | Add a list box to view the users collections | 1 | /
Create a collection | Add a button that opens a window for the user to enter collection info | 2 | /
Create a collection | Add a button that allows the user to delete the selected collection from the list box. | 2 | /
Add a series to their collection | Add a button that opens an add series window | 1 | /
Add a series to their collection | create an add series window that has appropriate controls for creating a series object | 1 | /
Delete a collection | Add a menu item that lets the user delete their collection | 1 | /
Delete a collection | Open a message box that asks if theyre sure that they want to delete the collection | 1
Sort my series alphabetically | add a series combobox that contains every series currently in the collection | 1
Sort my series alphabetically | only show the issues in the collection list that match the selected series | 2
| Estimate Totals | 15 | 0 | 0 | 0 | 0