## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Code Things…
Delete a collection | Empty the series list | 0.5
Delete a collection | Update the listview to reflect changes to the list | 0.5
Add a series to my collection/ manually enter a series | Take data from the textboxes on the create series window and make a new series object from it. | 0.5
Add a series to my collection/ manually enter a series | Add the new series to the series list. | 0.5
Add a series to my collection/ manually enter a series | Update the listview to reflect changes to the list | 0.5
Download the application from a webpage | Create a homepage using javascript | 1
Download the application from a webpage | Store the application in a download link that the user can click to download it. | 1
Download the application from a webpage | Host the webapp with Azure. | 1
Sort my series' alphabetically ascending | add a method to compare series object by their title and order them in the listview from A-Z. | 2
Sort my series' alphabetically descending | add a method to compare series objects by their ttle and order them in the listview from AZ-A. | 1
View the information about a series | Create a window that displays the series info | 1
View the information about a series | Open the window when the user selects a series and clicks the view button. | 0.5
Edit a series that’s in my collection | Create a window that displays the series info and allows the user to change the data. | 0.5
Edit a series that’s in my collection | Open the window when the user selects a series and clicks the edit button. | 0.5
Edit a series that's in my collection | Update the series that was edited in the listview | 0.5
Add a notes section for each series
Add a boolean setting for keeping track of owned and not owned series
Add filtering for owned series
| Estimate Totals | 11.5 | 0 | 0 | 0 | 0